## Slide 1
USASA Working Groups (WIG) Report
An organizational overview of the 2024-2025 Working Groups, Sub-WIGs, progress, and impact.
Working Groups WIG Initiative 2025
Presented to: USASA
Date: September 2025
United States Adult Soccer Association
Building Consistency & Accountability

## Slide 2
Agenda & Presentation Overview
1.
2.
3.
4.
Member Feedback
WIG High Level Structure
WIG 1 – 5 Details
Next Steps
Each Working Group (WIG) section includes:
Working Group Members
Meeting Dates & Frequency
Focus & Purpose
Timelines & Status Updates
Challenges, Feedback, Solutions & Member Benefits
Key Accomplishments
Current Priorities & Timeline
5.
Timeline & Progress

## Slide 3
USASA Working Groups: Timeline & Progress
Board – Interviews, Assessment, & 2 Day Strategy Session
Staff Development & Board Meeting
WIG Report & recommendation of WIG Working Groups sent to the Board
WIG Working Groups Implementation
Wildly Important Goals from Board:
Alignment & Structure
Partnerships & Sponsorships
Technology & Innovation
Engaged to work with Staff development & Membership Feedback
AGM – Membership Update, Feedback Session, & WIG Creation
Board Decision to move forward with WIG Working Groups
Beginning of Staff Interviews, Assessment, 2 Day Retreat & Sessions
Staff Top 5 Priorities:
Board Meeting:
Membership Interviews
Membership Feedback Report
Working Groups:
Board Focus Areas:
Organizational Mission & Vision
Roles & Responsibilities
Ways of Working
Member Value
Goals & Objectives
Sponsorships & Partnerships
Best Practices Framework
Improve Access to Playing
Revamp USASA Operating Model
Balance National & Local Support
Youth to Adult Bridge
Mission, Vision, & Values
Goals, Priorities, & Strategy
R&R, Communication, & Collaboration
Growth & Development
Membership
AGM – September 2025
WIG Working Group Report out
Staff & Board Recommendations
Path Forward
APRIL
MAY-AUG
OCT
JAN-AUG
MAY
SEP
DEC
CURRENT
2024
2025

## Slide 4
USASA Member Survey Assessment
Scoring Methodology
1
2
3
4
CRITICAL
CONCERNING
DEVELOPING
STRONG
1.00-1.99
2.00-2.49
2.50-2.99
3.00-4.00
CRITICAL AREAS (1.00-1.99)
USASA has adapted effectively to changes in the soccer landscape.
USASA serves different levels of membership equally.
USASA uses innovation (new programs, formats, and technology) to serve adult soccer.
1.72
1.89
2.00
CONCERNING AREAS (2.00-2.49)
There is a culture of accountability and follow-through at USASA.
As a member, I have the tools and resources needed from USASA.
USASA remains connected to its membership.
The USASA Board of Directors is willing and receptive to make necessary changes based on feedback.
USASA has established partnerships with other soccer associations (youth, collegiate, affiliate).
2.06
2.06
2.11
2.11
2.22

## Slide 5
USASA Survey Results: Key Themes from Members
Governance Concerns:
Need for term limits and strategic focus to bring fresh perspectives and improve board effectiveness.
Referee Crisis:
Overemphasis on National Tournaments:
Insufficient referees (30% decrease) impacting match quality and limiting membership growth potential.
Lack of Regional Support:
Significant disparities in resources and opportunities between regions, especially east vs. west coast.
Facilities Access:
Perceived neglect of grassroots soccer in favor of higher-level competitive events.
High costs and limited field availability are significantly restricting growth opportunities across regions.

## Slide 6
USASA Survey Results: Member Frustrations & Detailed Concerns
Top Frustrations
Investment in State Associations and Regions
On the Board:
On Lack of Change:
On Volunteers:
On Term Limits:
On Strategic Focus:
On Resource Disparities:
On State Associations:
On Disparities:
On National Focus:
On Facilities:
"I don't think the board is evil, and I don't want their job either, but they need to communicate more and be more accountable."
"We only look back. We need to look into the horizon and adapt to the changing soccer landscape."
"It's incredibly difficult to find volunteers, and USASA isn't doing enough to help us recruit new people."
"The Board is too operational and doesn't do enough advising. They need term limits to bring in fresh perspectives."
"USASA has not moved forward and needs to focus on making the game better for the average adult rec level soccer player."
"The way we do soccer on the west coast is different from the east coast, and we haven’t seen any change out here. We need more support.”
"Washington is exploring direct affiliation with the Federation because we’re not getting the support we need from USASA.”
"Field rentals are too expensive, and it's killing our ability to grow the sport, especially for recreational leagues."
Governance Concerns
"The way we do soccer on the west coast is different from the east coast, and we haven't seen any change out here."
"USASA's focus on national tournaments is leaving grassroots soccer behind. We need more support at the local level."
Regional Support & Facilities
On National Funding:
"The national funding needs to have greater appeal to everyone, not just those on the eastern seaboard."

## Slide 7
USASA Working Groups – Introduction
The USASA Working Group Initiative follows a structured, collaborative process to drive organizational improvement through member-focused projects:
Purpose & Formation
Identify and address key organizational priorities
Leverage diverse expertise across membership
Meeting Cadence & Milestones
Create actionable, measurable outcomes
Support USASA’s Mission to connect, build, and strengthen soccer communities
Working Groups finalized: December 10, 2024
Regular meetings: Monthly from January
US Soccer AGM: February 27-28, 2025
Deliverables: Now, end of 2025 & 2026
The 4D WIG Methodology
DESIGN
Working groups begin meetings to review initial suggestions, member feedback, and other opportunities.
DISCUSS
Working groups meet with key stakeholders to elicit feedback on deliverables and revise as needed.
DEBATE
DELIVER
Teams debate the various feedback elements and suggested changes before revising draft and recirculating.
Teams prepare final deliverables and present to Working Group Leadership & the USASA National Board of Directors.

## Slide 8
2024–2025 WIGs: High-Level Structure
WIG Focus Areas and Current Status:
1. SPONSORSHIP & PARTNERSHIP NETWORK
3. IMPROVE ACCESS TO PLAYING OPPORTUNITIES
Led by Bruce Bode
Led by Jen Sunderland
Goal: Establish strong sponsor programs and partnership networks
Goal: Improve member value by expanding access to playing opportunities
Current Focus:
Create and Implement a Best Practices Framework
Identify and Expand Soccer Playing Opportunities
SUB-WIG #1
Build Strategic Sponsorship Programs
2. BEST PRACTICES FRAMEWORK
Led by Cassie Stipe
Goal: Foster member engagement with standardized best practices
Current Focus:
SUB-WIG #1
Current Focus:
SUB-WIG #1
4. REVAMP USASA OPERATING MODEL
5. BALANCE NATIONAL EVENTS & LOCAL SUPPORT
Led by Ava Lynch
Led by Bruce Bode
Goal: Transform USASA into a modern member services organization
Current Focus:
Evaluate Resource Allocation
SUB-WIG #1
Realign Roles and Responsibilities
Goal: Ensure equitable resource allocation across all levels of play
Current Focus:
SUB-WIG #1
Working Group Process:
Each WIG is currently focused on its first Sub-WIG priority
Working groups follow a Design → Discuss → Debate → Deliver methodology
Deliverable timelines extend from present through 2026
Progress tracked via defined Key Results for each Sub-WIG

## Slide 9
WIG 1
Sponsorship & Partnership Network
Committee Members
Bruce Bode
Coco Moya
Jeremy Mikell
Richard Moeller
Michael Schecter
Brett Hurwitz
(Staff Lead)
(NBOD Liaison)
Meeting Schedule
Feb 4, 2025
Feb 18, 2025
May 27, 2025
Aug 26, 2025
Sep 16, 2025
Total: 5 meetings completed
Focus & Purpose
Identify and secure suitable national and regional sponsorships that connect with and support our soccer community to increase revenues and build individual membership value.
CURRENTLY FOCUSED ON
Sub-WIG #1: Build Strategic Sponsorship Programs
Develop sponsorship programs aligned with USASA's mission and strategic goals
Offer tailored packages for corporate, community, and nonprofit partners
Ensure sponsorship benefits are equitably distributed across the membership ecosystem
Additional Sub-WIGs:
Expand Partnerships with External Stakeholders
Increase Marketing and Communication Efforts
Mission: To connect, build, and strengthen soccer communities

## Slide 10
Challenges, Feedback, Solutions & Member Benefits
Challenges
Solutions
Feedback Collection
Member Benefits
Creating staffing capacity for project
Identifying what makes USASA attractive to sponsors
Need for updated marketing/pitch materials
Connecting with appropriate external partners
Diversifying revenue streams across membership
Balancing national and regional sponsorship needs
Creation of Brand Bullseye identifying key USASA attributes
Outside agency RFPs for sponsorship acquisition
Comprehensive revision of sponsor pitch materials
Identified sponsor targets across business categories
Database rehabilitation for improved targeting and analytics
Input from potential sponsors on value propositions
Review of past USASA pitch materials effectiveness
Evaluation of member database for sponsor targeting
Assessment of outside agency proposals
National and regional member perspective on partnerships
New Funding Sources:
Partners increase organizational revenue by Q1 2026
Enhanced Member Value:
Individual discounts and special access by Q4 2025
Strategic Partnerships:
National & Regional Impact:
Supporting soccer communities nationwide
Benefits across the membership ecosystem
WIG 1

## Slide 11
WIG 1
Key Accomplishments & Narrative Context
Key Accomplishments
Rehabilitated Player Member Database for newsletter and management use
Evaluated what makes USASA an attractive partner for sponsors
Created a Brand Bullseye identifying key attributes of USASA
Solicited proposals from outside agencies for sponsorship acquisition
Began identifying categories and potential sponsor targets
Reviewed past USASA pitch materials and revised information
Narrative Context
The WIG 1 Working Group began building the foundation for seeking appropriate sponsor relationships that can support and connect our soccer communities.
It did so by taking a deep dive into what USASA looked like to those inside and outside the USASA membership. After creating a Brand Bullseye the group began looking at the type of sponsor that would be a good fit.
By identifying what potential sponsors could bring to our membership, we started identifying types of sponsors and some individual organizations. This was done from a national and regional perspective.
Sales materials previously developed by USASA were reviewed and revisions were discussed. Proposals from two outside agencies for sponsor acquisition have been received and are being evaluated by staff.

## Slide 12
Current Priorities & Timeline
Current Priorities
Select outside agency to identify and solicit potential sponsors
Identify sponsor targets and business categories
Complete sponsor agreements for revenue and membership value
Develop revised sponsor pitch materials
Key Focus
2 sponsor agreements that increase individual membership value (Q4 2025)
2 sponsor agreements that add to and diversify USASA revenue stream (Q1 2026)
Timeline
Completed
End of 2025
2026
Brand Bullseye creation identifying key USASA attributes
Rehabilitated Player Member database for management
Select outside agency to identify for sponsorship acquisition
Identify potential sponsor targets and business categories
Complete 2 sponsor and/or advertising agreements that increase individual membership value (e.g., discounts, preferred pricing, preferred access).
Complete 2 sponsor agreements that add to and diversify USASA revenue stream.
WIG 1

## Slide 13
WIG 2
Best Practices Framework
Committee Members
Cassie Stipe
Audrey Wilson
Tom Moore
David Borts
Kevin Anderson
Kasha Roberts
Nick Calabro
Robin Runstein
(Staff Lead)
(NBOD Liaison)
Meeting Schedule
Jan 14, 2025
Feb 4, 2025
May 13, 2025
Jul 16, 2025
Jul 30, 2025
Aug 13, 2025
Aug 27, 2025
Sep 10, 2025
Total: 8 meetings completed
Focus & Purpose
Define and create an education and training program for governance and administration. Utilize surveys and feedback sessions to validate member priorities and identify subject matter experts.
CURRENTLY FOCUSED ON
Sub-WIG #1: Create & Implement Best Practices Framework
Develop and distribute best practices for governance, event management, marketing, and member services
Standardize and organize resources to support member implementation of best practices
Promote "communities of interest" as a cost-effective and sustainable way to connect members
Additional Sub-WIGs:
Enhance Member Resource Center
Develop Educational Program Framework
Implement Branding, Marketing, and Website Strategies
Mission: To connect, build, and strengthen soccer communities

## Slide 14
Challenges
Solutions
Feedback Collection
Member Benefits
Balancing resources with organizational capacity
Identifying top priorities from 50+ potential topics
Aligning strategies with diverse member needs
Ensuring consistent branding and communication
Meeting expectations with limited staff resources
Addressing different knowledge levels across membership
Education Program framework with multi-level training
Member Resource Center comprehensive overhaul
"Communities of interest" for knowledge sharing
Structured priorities in 7 knowledge categories
Consistent meeting cadence to maintain momentum
Comprehensive surveys and member discussions
Staff coordination and resource assessment
AGM panel presentation and feedback sessions
Validation of member priorities through direct input
Accessible Training:
Customized for all governance levels
Improved Resources:
Enhanced discoverability and organization
Knowledge Sharing:
Enhanced Engagement:
Best practices across leagues and states
Improved member services and support
WIG 2
Challenges, Feedback, Solutions & Member Benefits

## Slide 15
Key Accomplishments & Narrative Context
Key Accomplishments
Developed and refined a comprehensive list of over 50 potential training topics in 7 categories
Narrowed priorities through surveys and discussions
Created Educational Program Framework
Prioritized Member Resource Center updates
Established consistent meeting cadence to maintain momentum
Coordinated with staff to align initiatives with organizational resources
Narrative Context
Throughout 2025, the WIG 2 Working Group has moved from idea generation to execution. The group focused on deliverables that align with USASA's capacity and priorities.
A key breakthrough has been the Education Program framework, which aims to deliver multi-level training opportunities for boards, state associations, and leagues. The Member Resource Center was also identified as a critical area for improvement.
The committee further recognized the importance of consistent branding and social media strategies.
The upcoming AGM will serve as a milestone, featuring a dedicated panel presentation and survey to validate member priorities and capture feedback. These efforts will guide the next 12 months of work, laying a foundation for impactful member services and best practices.
WIG 2

## Slide 16
Current Priorities & Timeline
Current Priorities
Education Program Development
Resource Center Overhaul
Refine knowledge areas across 7 categories
Assign training levels for boards, states, and leagues
Determine optimal delivery methods
Continue organizing resources by category
Define format for more accessible navigation
Member Engagement
Create helpful resource hub with search capability
AGM survey with participation incentives
Build communities of interest
League connection through state intermediaries
Timeline & Key Results
Completed
End of 2025
2026
AGM panel presentation & member survey to validate priorities and capture feedback
Complete Resource Center overhaul implementation with organized content and improved navigation
Launch comprehensive Member Resource Center with best practices content
Continue Best Practices implementation across entire organization with multi-level training opportunities
WIG 2

## Slide 17
WIG 3
Improve Access to Playing Opportunities
Committee Members
Jen Sunderland
Rocco Avallone
Jono Rollins
Nate Shotts
Justin Woodside
Otey Smithson
(Staff Lead)
(NBOD Liaison)
Meeting Schedule
Dec 17, 2024
Jan 8, 2025
Feb 12, 2025
Feb 19, 2025
May 28, 2025
Aug 27, 2025
Sep 10, 2025
Total: 7 meetings completed
Focus & Purpose
Build a clear, scalable pathway for U17–U19 players to transition from youth soccer into adult participation—keeping them connected to the game and community.
CURRENTLY FOCUSED ON
Sub-WIG #1: Youth-to-Adult Transition Pathway
Survey membership to identify existing and potential playing opportunities
Support new initiatives for member growth and access
Bridge the gap between youth and adult soccer participation
Additional Sub-WIGs:
Bridge Gaps in Member Access
Support Member Growth and Participation
Mission: To connect, build, and strengthen soccer communities

## Slide 18
Challenges
Solutions
Feedback Collection
Member Benefits
Significant engagement drop-off post-youth soccer
Limited awareness of adult playing opportunities
Logistical barriers (travel, team formation)
Financial constraints for young adults
Traditional formats not always appealing to youth
Small-sided format events (5v5, 7v7, 8v8) as entry points
Cost reduction incentive programs
Modern social outreach (Instagram, TikTok, Snapchat)
"Next Step Soccer" guide development
Direct partnerships with youth organizations
Member organization survey (limited response)
Soccer is Life 8v8 Tournament pilot learnings
Playing format preferences assessment
Youth-to-adult transition gap analysis
Player Retention:
Ecosystem Support:
Sustained participation beyond youth soccer
Connected Pathway:
Seamless transitions between age groups
Growth Driver:
Membership growth and retention
Strengthened soccer community
WIG 3
Challenges, Feedback, Solutions & Member Benefits

## Slide 19
Key Accomplishments & Narrative Context
Key Accomplishments
Approved three primary goals: expanding opportunities, increasing participation, and strengthening partnerships
Piloted the Soccer is Life 8v8 Tournament, which highlighted the need for longer lead times to ensure success
Created 12 How-To Guide topics (tournaments, leagues, insurance, facilities, membership value) for Best Practices
Launched a member survey to capture what formats are being played across member organizations
Shifted focus to bridging the gap between youth and the adult game
Narrative Context
The WIG 3 Working Group has transitioned from resource development to a vital new focus: bridging the gap between youth and adult soccer.
Drawing on lessons from pilot events and the development of How-To Guide topics (now transferred to WIG 2 for Best Practices), the group is working to establish clear pathways that keep players engaged beyond U19.
This initiative directly supports USASA's mission to Connect, Build, and Support soccer communities in the U.S. and advances our vision to maximize the adult soccer experience.
By emphasizing early engagement, accessible playing formats, strong partnerships, and modern marketing strategies, WIG 3 is helping USASA welcome the next generation of players and ensure the sport's sustained growth.
WIG 3

## Slide 20
Current Priorities & Timeline
Current Priorities
Education Program Development
Event & Format Development
Identify and engage four organizations to strengthen our connected network
Design programs that reduce cost and awareness barriers for young players
Pilot small-sided formats (5v5, 7v7, 8v8) as fun, flexible entry points
Resource Development
Share transition success stories across platforms
Launch Next Step Soccer guide for U17–U19 players
Reach younger audiences through modern social media platforms
Timeline & Key Results
Completed
End of 2025
2026
Survey member organizations to identify playing format preferences
Create 12 How-To Guide topics for Best Practices inclusion
Establish partnerships with 4 youth organizations for transition pathway
Launch Next Step Soccer guide for U17-U19 players
Pilot small-sided format events as youth-to-adult transition on-ramps
WIG 3

## Slide 21
WIG 4
Revamp USASA Operating Model
Committee Members
Ava Lynch
Roy Carlson
Elaine Freedman
Jeremy Poklemba
MaryBeth Falk
(Staff Lead)
(NBOD Liaison)
Meeting Schedule
May 5, 2025
June 2, 2025
Aug 26, 2025
Sep 9, 2025
Total: 4 meetings completed
Focus & Purpose
Analyze and evaluate efficiency and effectiveness of the different elements of USASA's operating model and identify gaps and inconsistencies to streamline the processes within the organization.
CURRENTLY FOCUSED ON
Sub-WIG #1: Realign Roles and Responsibilities
Clarify and streamline roles & responsibilities within USASA's membership
Reduce overlap and improve decision-making processes
Transition the National Board of Directors to a more strategic and advisory role
Additional Sub-WIGs:
Establish Feedback Systems
Succession & Leadership Development
Mission: To connect, build, and strengthen soccer communities

## Slide 22
Challenges
Solutions
Feedback
Member Benefits
Complex committee structures and processes
Role overlaps and responsibility gaps
Need for transparency in governance
Process inefficiencies across operations
Gaps and inconsistencies in organizational model
Committee realignment and structure optimization
Nomination process development and standardization
Standardized frameworks and committee charters
Comprehensive communication plan implementation
Structured surveys and feedback collection systems
NBOD surveys and leadership assessments
Committee member and chair input collection
USASA member organization feedback analysis
Cross-functional perspective gathering
Ongoing stakeholder engagement process
Streamlined Operations:
Enhanced Effectiveness:
More efficient processes and decision-making
Clearer Roles:
Reduced overlap and better accountability
Improved Governance:
More transparent committee structure
Better alignment with strategic goals
WIG 4
Challenges, Feedback, Solutions & Member Benefits

## Slide 23
Key Accomplishments & Narrative Context
Key Accomplishments
Approved three primary goals: roles and responsibilities, feedback systems, and succession & leadership development
Determined committee realignment as first focus area to streamline processes
Created and distributed comprehensive surveys to NBOD, Committee Members/Chairs, and USASA Members
Established structured feedback collection process to guide future recommendations
Narrative Context
The WIG 4 Working Group has begun working underneath their first focus (Realign Roles and Responsibilities) by addressing the committees and their structures within USASA.
With such vast focuses and workflows being conducted by each individual committee, the group has been evaluating areas that need improvement to help USASA function more effectively on a larger scale.
Now in the feedback collection process, the Working Group is focused on hearing thoughts from various perspectives, and using that to help guide what their recommendation will be for realigning the committees to a new and more efficient structure.
Ultimately, this work is a strong step in ensuring USASA follows through on their vision: maximizing the adult soccer experience.
WIG 4

## Slide 24
Committee Charter Template
Committee Name:
[Enter committee name]
Purpose & Scope
Goals & Objectives
Member Roles
Meetings & Reporting
Committee Purpose:
Scope of Authority:
[Enter the primary purpose of this committee]
[Define committee's authority and limitations]
[List key member responsibilities]
[Describe reporting process]
Goal 1:
Success Metric:
Meeting Frequency:
Meeting Format:
[Enter goal]
[How measured?]
[e.g., Monthly]
[e.g., Virtual]
Goal 2:
Success Metric:
[Enter goal]
[How measured?]
Chair:
Board Liaison:
Staff Liaison:
[Name]
[Name]
[Name]
Key Responsibilities:
Reporting Structure:
Committee Chair Signature:
Board Approval Signature:
Charter Review Date:
Date: ___/___/_____
Date: ___/___/_____
[Next review date]
United States Adult Soccer Association
Committee Framework Initiative 2025

## Slide 25
Action Plan Format Template
Phase-Specific Objectives
Resources Needed & Constraints
Task Assignments & Timelines
Phase:
Key Outcomes Expected:
Resources Required:
Select Phase
(Discover, Design, Discuss, Do, Deliver)
Enter main objective for this phase...
List 3-5 key outcomes expected from this phase...
List people, budget, tools, and other resources needed...
Known Constraints:
Dependencies:
Document limitations...
List external dependencies...
Task Description
Owner
Due Date
Status
Success Metrics & Milestones
Key Performance Indicators (KPIs):
Define specific measurable indicators of success...
Key Milestones:
Target Completion:
List important milestones...
Enter final deadline...
Task 1
Owner
MM/DD/YY
Not Started
Task 2
Owner
MM/DD/YY
Not Started
Task 3
Owner
MM/DD/YY
Not Started
Task 4
Owner
MM/DD/YY
Not Started
Task 5
Owner
MM/DD/YY
Not Started
Add or remove rows as needed
United States Adult Soccer Association
Committee Framework Initiative 2025

## Slide 26
Progress Report Template
Committee Name:
Reporting Period:
Chair:
Report Date:
Status Updates Against Timeline
Achievement Tracking
Current status and progress against timeline
Task/Milestone
Target Date
Status
%
Completed objectives/tasks and key achievements
1.
2.
3.
Risk Identification
Resource Utilization Summary
Identify any issues, risks or blockers
Summarize used and remaining resources
Risk/Issue
Impact
Mitigation
Owner
Budget Utilization:
Time/People Resources:
Allocated:
Spent:
Remaining:
People Assigned:
Hours Utilized:
Additional Resource Notes:
United States Adult Soccer Association
Committee Framework Initiative 2025
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
Click to add text
x%
x%
x%
Click to add text
Click to add text

## Slide 27
Self-Assessment Tool Template
Committee Effectiveness Survey
Member Contribution Evaluation
Process Improvement Indicators
Rate overall effectiveness (1=Poor, 5=Excellent):
Most effective practices:
Areas for improvement:
1
2
3
4
5
Click to add text
Click to add text
Member Name
Role
Rating
Name
Role
Name
Role
Name
Role
E
M
N
Exceeds
Meets
Needs
Meeting Efficiency
Meetings on time
Clear agenda
1
2
3
4
5
1
2
3
4
5
Impact Measurement Guide
Suggested process improvements:
Documentation
Clear notes
Timely communication
1
2
3
4
5
1
2
3
4
5
Click to add text
Goal Achievement
100% (All goals)
75% (Most goals)
50% (Half of goals)
25% (Few goals)
0% (No goals)
Deadlines Met
Stakeholder Rating
New Ideas
5+ ideas implemented
3-4 ideas implemented
1-2 ideas implemented
0 ideas implemented
E
G
F
P
VS
S
N
D
Excellent
Good
Fair
Poor
Very Satisfied
Satisfied
Neutral
Dissatisfied
United States Adult Soccer Association
Committee Framework Initiative 2025
E
M
N
Exceeds
Meets
Needs
E
M
N
Exceeds
Meets
Needs
Click to add text

## Slide 28
Current Priorities & Timeline
Current Priorities
Committee Structure Analysis
Feedback Collection
Process Improvement & Communication
Establishing an understanding of areas covered by committees
Mapping committee structures and workflows
Continuing to survey membership for stronger data
Hearing perspectives from all stakeholders
Identifying areas within committee processes for improvement
Maintaining communication through various channels
Ensuring transparency with those affected
Timeline & Key Results
Completed
End of 2025
2026
Completed
End of 2025
2026
Survey all committees on current roles and responsibilities
Evaluate effectiveness and refine as needed
Create and implement a standardized committee framework
Revise, update, and approve committee charters
Implement new committee structure and processes
WIG 4

## Slide 29
WIG 5
Balance National Events & Local Support
Committee Members
Bruce Bode
Jeff Berman
Ron Burnett
Dennis Pope
Michael Tata
NBOD Liaison
(Staff Lead)
Meeting Schedule
Jan 30, 2025
May 20, 2025
Sep 18, 2025
Total: 3 meetings completed
Focus & Purpose
Ensure USASA's resources and attention are allocated equitably between national tournaments and grassroots soccer, delivering support for all levels of play.
CURRENTLY FOCUSED ON
Sub-WIG #1: Evaluate Resource Allocation
Review allocation of resources between national tournaments and member services
Develop review program process to ensure inclusion and equity
Develop database of ongoing tournaments and events
Additional Sub-WIGs:
Foster Grassroots Growth
Encourage Participation Across All Levels
Mission: To connect, build, and strengthen soccer communities
Feb 2, 2025

## Slide 30
Challenges
Solutions
Feedback Collection
Member Benefits
Resource allocation balance between national tournaments and local initiatives
Ensuring inclusion and equity across diverse membership
Managing national vs local priorities effectively
Creating sustainable program evaluation processes
Balancing competition needs with grassroots development
Develop review program process to ensure inclusion and equity
Create comprehensive national event database
Establish program review framework with clear criteria
Design submission process for new or expanded programs
Implement equitable resource allocation methodology
Member program submissions and suggestions
Structured review process feedback loops
State association input on resource allocation
Tournament organizers and participants evaluations
Cross-membership assessments of program equity
Equitable Resource Distribution:
Transparent Process:
Better balanced resources across regions
Improved Program Access:
Enhanced availability for all membership levels
Balanced Support:
Meeting both national and local needs
Clear criteria for program evaluation
WIG 5
Challenges, Feedback, Solutions & Member Benefits

## Slide 31
Key Accomplishments & Narrative Context
Key Accomplishments
Resource allocation evaluation initiated across national events and local programs
Review framework development for program assessment started
Initial assessment of tournament and event data collection methods
Engaged with member organizations to strengthen grassroots participation
Narrative Context
The WIG 5 Working Group has focused on balancing USASA's resources between national tournaments and grassroots soccer support—ensuring equitable allocation to all levels of play.
Through assessment of current resource distribution, the team has identified opportunities to better serve diverse membership needs, from competitive events to local initiatives.
The group has begun developing a review process for inclusion and equity across programs, while creating a database of tournaments and events to understand the full landscape of activities.
These efforts will enable USASA to maximize impact at all levels, creating participation pathways while maintaining high-quality national tournaments that showcase adult soccer excellence.
WIG 5

## Slide 32
WIG 5
Current Priorities & Timeline
Current Priorities
Resource Allocation Evaluation
Develop review program process to ensure inclusion and equity
Develop database of ongoing tournaments and events
Program Development
Create framework for equitable resource distribution
Establish grassroots participation initiatives
Timeline & Key Results
Completed
End of 2025
2026
Review current resource allocation structure
Finalize and present a national event database concept
Support the development of a program review framework
Identify review criteria for new member support programs
Create a submission and review process for new or expanded member programs

## Slide 33
Next Steps
Continue Working Groups
Member Recruitment
Working Groups will continue through the end of the year with the current members.
Moving into the next year, we will need to add or replace members. If you have an interest in joining a WIG Working Group, please let us know.
Monthly Website Updates
Quarterly Board Announcements
Each month the Website will be updated with current progress and results from WIG Working Groups.
Major WIG updates will be announced at the Quarterly Board Meetings.
WIG Lifecycle Management
Once a WIG is complete, or folds under another WIG, we will start a new WIG.
All WIGs advance our mission to Connect, Build, and Support soccer communities
Membership Execution & Feedback
Once we create resources, blueprints, or partnerships for members, please use and give us feedback on your results